PROJECT REPORT

Volve Field: Drilling Non-Productive Time vs. Well Productivity

An end-to-end analytics project: Python  →  PostgreSQL  →  Power BI

Author:  Utkarsh Raj Srivastava

Date:  October 2026

Repository:  github.com/utkarshraj94/volve-npt-analysis

Data:  Equinor Volve open dataset (daily drilling reports and production data)

Purpose:  Educational / portfolio, non-commercial

Contents

Note: if the page numbers above are blank, right-click the table and choose Update Field.

# 1. Executive Summary

This project measures how much of the Volve drilling campaign was lost to non-productive time (NPT), where that time went, what it plausibly cost, and whether the wells that were hardest to drill were also the wells that produced the least. The work runs from raw daily drilling reports through a classified, audited dataset, a PostgreSQL star schema and a five-page Power BI report.

### Headline results

| Measure | Result |
| --- | --- |
| Logged rig time analysed | 39,395 hours across 26 wellbores and 1,750 daily reports (1992–2016) |
| Non-productive time | 7,888 hours = 20.0% of logged time (± about 0.2 percentage points) |
| Productive time | 30,510 hours = 77.4% |
| Rig moves / mobilisation | 997 hours = 2.5% (kept separate from both) |
| Where the NPT went | Surface-equipment repair (36.9%) and weather (24.5%) together account for 61.4% of all NPT |
| Concentration | 13 of 26 wellbores account for 82% of all NPT hours |
| Modelled cost of NPT | About $98.6M at an assumed $12,500 per rig-hour (a modelling assumption, not a reported figure) |
| NPT vs. production | Among the six wells with oil data, high NPT did not go with low output (small sample; see Section 7) |

### Main conclusions

- One in five logged rig hours was non-productive. Most of it came from two causes that are largely outside the well itself: surface-equipment maintenance and weather.

- NPT was uneven. A few short or exploratory wellbores (19-B at 78.5%, F-11 at 56.2%) had extreme rates, while 13 wellbores carried 82% of the lost hours.

- The data does not support the idea that high NPT meant low production. F-11 lost 56.2% of its rig time yet produced 7.2 million barrels, and the largest producer (F-12) ran at 17.9%. Only six wells have oil data, so this is a pattern to note, not a proof.

- The classification behind the 20.0% figure is auditable: a human reviewed 1,517 rows, and the high-confidence tier showed a 0% error rate in its audit sample.

# 2. Background and Objectives

## 2.1 Business question

Drilling is expensive, and time spent not making progress is the most visible source of avoidable cost. The Volve field (Norwegian North Sea, operated by Equinor until 2016) published its daily drilling reports and production history as an open dataset. That makes it possible to ask a concrete question: where did the downtime go, what did it plausibly cost, and did high-NPT wells deliver proportionally higher production?

## 2.2 Objectives

- Extract and clean the daily drilling reports and the production history into analysis-ready tables.

- Define NPT in a way that can be defended, classify every logged activity against it, and measure how reliable the classification is.

- Load the result into a PostgreSQL star schema that supports repeatable analysis.

- Quantify NPT by category, wellbore, hole section and year, and attach a modelled cost.

- Test, descriptively, whether NPT intensity relates to production output.

- Present the findings in an interactive Power BI report.

## 2.3 Scope

This is a descriptive operational review of 26 wellbores. It is not a statistical or predictive study, and cost figures are modelled. These limits are stated again, with their consequences, in Section 7.

# 3. Data Sources

All data comes from the Volve dataset released by Equinor ASA and the former Volve licence partners for study and research. Raw files are not committed to the repository, in line with the licence. See LICENCE-DATA.md.

| Source | Content | Size and coverage |
| --- | --- | --- |
| Daily drilling reports (HTML) | Operations table per day: time range, main activity, activity code, state (ok/fail), narrative, depth, hole section | 1,759 files; 1,750 with an operations table; 23,447 activity rows; 26 wellbores; reports dated 1992–2016 |
| Production data (Excel) | Daily allocated oil, gas, water and water-injection volumes, on-stream hours, pressures, well type and flow kind | 15,634 daily rows; 7 wellbores; 2007-09 to 2016-12 |
| Reference tables (created) | wellbore_map.csv (26 wellbores, parent well, production flag) and npt_taxonomy.csv (32 NPT category rows) | Versioned in the repository |

## 3.1 Data quality findings

### Production data

- No duplicate (date, wellbore) rows. 18 rows where well type and flow kind disagree; 4 negative water-volume rows.

- Date coverage per wellbore has gaps of up to 85 days (F-12 and F-14).

- Only 7 wellbores have production data, and F-4 is a water injector with no oil volume.

### Drilling reports

- 9 reports have no operations table. These contribute no hours.

- 220 of 1,750 reports (12.6%) do not sum to 24 hours. Confirmed causes: rig-move handovers split one calendar day across two well files, and small 15-minute gaps from manual report compilation. Every shortfall is an exact multiple of 0.25 hours, so this is not a parsing error. NPT is therefore always summed from the logged hours, never assumed from 24 per report.

- 265 of 1,822 actual-drilling rows show depth decreasing against the previous drilling row for the same well. This was recorded as a data characteristic and does not affect the NPT hours.

# 4. Methodology

## 4.1 Project phases

| Phase | Work | Main output |
| --- | --- | --- |
| 0 | Scaffold, schema design, environment | README, requirements, .env pattern |
| 1 | File inventory of the dataset | docs/file_inventory.csv |
| 2 | Production data cleaning | data/interim/production_clean.parquet (15,634 rows) |
| 3 | HTML report parsing; phase and state extraction; NPT signal diagnostics | data/interim/drilling_activity.parquet |
| 4 | Rule-based NPT classification and 1,517-row manual review | drilling_activity_final.parquet; docs/npt_taxonomy.md |
| 5 | PostgreSQL star schema, idempotent ETL, analytical views, seven analysis queries | sql/ scripts; src/05_load_to_postgres.py |
| 6 | Power BI data model, DAX measures and five-page report | powerbi/volve_npt.pbix; volve_theme.json |

## 4.2 Defining NPT

Phase 3 produced two candidate signals that disagreed by a factor of six: the source’s own per-row state flag (state = fail), covering 3.2% of hours, and the interruption main activity, covering 21.2% of hours. Neither was used directly. The final definition is a hybrid:

- A row is NPT if its final Level-1 category starts with “NPT”. Classification is driven by the specific activity and its narrative, not by a single source column.

- Rig moves and mobilisation are a separate third category. A rig skid between wells is neither progress nor failure, so about 997 hours are excluded from both productive and NPT.

- Planned and corrective work are told apart by narrative. Circulating for a planned bottoms-up is productive; circulating to clear a pack-off is NPT. A planned geological sidetrack is productive; a sidetrack after losing the hole is NPT.

- The source fail flag is an override. A row the source marked as failed is promoted to NPT even if the keyword rules called it productive.

## 4.3 Classification and audit

Classification ran in three re-runnable stages. A rule-based pass (src/04_classify_npt.py) applied activity-code lookups, then narrative keyword matching, then the fail override, giving each row a Level-1 and Level-2 label and a confidence of high, medium or low. A manual review then covered every low-confidence NPT-flavoured row plus fixed-size samples of the other tiers, 1,517 rows in total. A finalisation step (src/04b_apply_review.py) applied the corrections and recorded, for every row, whether a human verified it.

| Confidence tier | Rows reviewed | Overridden | Error rate |
| --- | --- | --- | --- |
| High | 150 | 0 | 0.0% |
| Medium | 150 | 66 | 44.0% |
| Low | 1,217 | 1,137 | 93.4% |

Table 4.1: Manual-review error rate by confidence tier (share of reviewed rows the human overrode).

The confidence tiers behaved as intended: the rules were reliable where they said they were, and wrong where they said they were unsure. Rule labels alone gave 21.70% NPT; after review the figure is 20.02%.

Residual uncertainty About 2,462 low-confidence productive-flavoured rows (2,180 hours) were sampled, not fully reviewed. Only 6 of 150 sampled rows (about 4%) were hidden NPT. Extrapolated, at most about 87 hours (0.2 percentage points) of NPT could remain hidden, hence the headline of 20.0% ± 0.2.

## 4.4 Data warehouse (PostgreSQL star schema)

The cleaned data is loaded into PostgreSQL 18 by src/05_load_to_postgres.py, which is idempotent: it drops and recreates the schema, loads the tables and rebuilds the views on every run.

| Table | Rows | Purpose |
| --- | --- | --- |
| fact_drilling_activity | 23,447 | One row per logged activity: hours, phase, NPT category, narrative, confidence, classification source |
| fact_daily_production | 15,634 | One row per well per day: oil, gas, water, injection, on-stream hours, pressures |
| dim_wellbore | 26 | Wellbore key, parent well, sidetrack, exploration and production flags |
| dim_npt_category | 31 | Level-1 / Level-2 taxonomy with is_npt and is_rig_move flags |
| dim_date | 9,862 | Calendar attributes |
| dim_hole_phase | 10 | Hole section (for example 8.5 in hole) and phase type |

Table 4.2: Star schema. Both fact tables share dim_wellbore and dim_date.

Five views support the analysis: v_npt_by_wellbore, v_npt_pareto, v_npt_cost, v_wellbore_production and v_npt_vs_production. Sidetracks are separate wellbores with the parent well kept as a roll-up attribute.

## 4.5 Power BI report

The report imports the six tables from PostgreSQL (Import mode). Four relationships were auto-detected, all one-to-many with single-direction filtering, and dim_date connects to both fact tables, so there are no ambiguous filter paths. dim_date is marked as the date table and raw key columns are hidden from report view. All logic lives in DAX measures held in a dedicated _Measures table (Appendix B), and the measures were validated against the database views before any visual was built. A custom theme (powerbi/volve_theme.json) and a shared header with page navigation give the five pages a consistent look.

# 5. Results

How percentages are defined Throughout this report, NPT % = NPT hours divided by total logged hours (including rig-move time in the denominator). This matches the 20.0% headline and the Power BI measure. The SQL view v_npt_by_wellbore uses a slightly different denominator (it excludes rig moves), which gives 20.5% field-wide. See Section 7.

## 5.1 Where the hours went

| Category | Hours | Share of total |
| --- | --- | --- |
| Productive | 30,509.7 | 77.4% |
| NPT (all sub-categories) | 7,888.3 | 20.0% |
| Rig move / mobilisation | 997.0 | 2.5% |
| Total logged | 39,395.0 | 100% |

Table 5.1: Hours by top-level category.

## 5.2 NPT Pareto: what caused it

| Level 1 | Level 2 | Hours | % of NPT | Cumulative |
| --- | --- | --- | --- | --- |
| NPT - Surface Equipment | Repair/Maintenance | 2,914.9 | 36.9% | 36.9% |
| NPT - External | Weather | 1,933.3 | 24.5% | 61.4% |
| NPT - External | Labor Action | 746.0 | 9.5% | 70.9% |
| NPT - Downhole Equipment | Fishing | 581.3 | 7.4% | 78.3% |
| NPT - Downhole Equipment | Failure | 426.9 | 5.4% | 83.7% |
| NPT - External | Materials/Logistics | 295.2 | 3.7% | 87.4% |
| NPT - Other | HSE/Permits | 258.1 | 3.3% | 90.7% |
| NPT - Other | Operational Failure | 211.0 | 2.7% | 93.4% |
| NPT - Wellbore | Hole Instability | 192.2 | 2.4% | 95.8% |
| NPT - Wellbore | Losses | 162.5 | 2.1% | 97.9% |
| Other categories (4) | Well control, unclassified, waits, corrective sidetrack | 167.0 | 2.1% | 100% |

Table 5.2: NPT hours by category, largest first. Cumulative column is the Pareto line.

Two categories explain over 60% of all NPT, and five explain 83.7%. The Labor Action category is a single documented event: an oilfield-services strike that suspended operations across 32 well-days (746 hours), which is better read as an outlier than as a recurring cause.

## 5.3 NPT by wellbore

| Wellbore | Type | Total hrs | NPT hrs | NPT % | Note |
| --- | --- | --- | --- | --- | --- |
| 19-B | Exploration | 617 | 485 | 78.5% | Short well |
| F-11 | Development | 390 | 219 | 56.2% | Short well |
| 19-A | Exploration | 2,590 | 994 | 38.4% | Most NPT hours |
| F-15-C | Development | 1,820 | 505 | 27.7% |  |
| 19-BT2 | Exploration | 1,455 | 395 | 27.1% |  |
| F-4 | Development | 2,858 | 697 | 24.4% | Water injector |
| F-12 | Development | 3,764 | 675 | 17.9% | Largest producer |
| F-14 | Development | 2,946 | 383 | 13.0% | Most efficient |
| F-5 | Development | 2,171 | 219 | 10.1% |  |
| F-1-A | Development | 155 | 6 | 3.9% | Lowest; tiny well |

Table 5.3: Selected wellbores, worst to best (10 of 26). Full list in the report page and database view.

- The five exploration wellbores average 29.8% NPT (2,604 of 8,733 hours) against 17.2% for the 21 development wellbores (5,285 of 30,662 hours).

- The exploration effect is not uniform: 19-B and 19-A are high, but 19-ST2 (19.3%) is about average and 19-S (14.2%) is below average.

- The two highest rates (19-B and F-11) are on short wells of under 650 hours each, so a few bad days move the percentage a lot. Absolute hours tell a different story: 19-A, F-4 and F-12 lost the most time.

- Concentration: the 13 worst wellbores by NPT hours account for 82.3% of all NPT.

## 5.4 NPT by hole section

| Hole section | NPT hrs | Total hrs | NPT % |
| --- | --- | --- | --- |
| post-completion | 2,753 | 8,610 | 32.0% |
| 8.5 in hole | 2,517 | 9,086 | 27.7% |
| 12.25 in hole | 843 | 4,857 | 17.3% |
| 17.5 in hole | 552 | 3,590 | 15.4% |
| 26 in hole | 431 | 2,335 | 18.4% |
| 36 in hole | 274 | 1,273 | 21.5% |
| 6 in hole | 211 | 942 | 22.4% |
| plug abandon | 291 | 4,277 | 6.8% |

Table 5.4: NPT by hole section (sections with under 30 hours and rows with no section omitted).

The post-completion phase (workover and interventions) and the 8.5-inch section are the two heaviest in absolute hours. Plug-and-abandon is the cleanest at 6.8%. The completion phase logs 4,136 hours with no NPT assigned and is omitted from the table.

## 5.5 Annual trend

| Year | NPT % | Year | NPT % | Year | NPT % |
| --- | --- | --- | --- | --- | --- |
| 1992 | 13.3% | 2008 | 17.5% | 2014 | 19.5% |
| 1993 | 21.0% | 2009 | 10.7% | 2015 | 15.8% |
| 1997 | 42.7% | 2010 | 14.8% | 2016 | 21.0% |
| 1998 | 21.9% | 2012 | 12.4% |  |  |
| 2007 | 14.0% | 2013 | 20.5% |  |  |

Table 5.5: NPT % by year. Years with no drilling reports (1994–96, 1999–2006, 2011) do not appear.

The 1997 exploration campaign is the outlier at 42.7%. From 2007 to 2016 the rate moved between about 11% and 21% with no clear improving trend; 2009 was the best year at 10.7%.

## 5.6 Modelled cost

| Wellbore | NPT hours | Modelled cost | Share of total |
| --- | --- | --- | --- |
| 19-A | 994 | $12.4M | 12.6% |
| F-4 | 697 | $8.7M | 8.8% |
| F-12 | 675 | $8.4M | 8.6% |
| 19-ST2 | 572 | $7.1M | 7.2% |
| F-15-C | 505 | $6.3M | 6.4% |
| All 26 wellbores | 7,888 | $98.6M | 100% |

Table 5.6: Modelled NPT cost = NPT hours x $12,500 per hour. The rate is an assumption (Section 7).

## 5.7 NPT versus production

Production volumes come from the six wellbores with oil output. F-4 is a pure water injector and is excluded. F-1-C and F-5 also carry some injection rows later in life.

| Wellbore | NPT % | Cum. oil (M bbl) | NPT hrs | NPT hrs per 1,000 bbl |
| --- | --- | --- | --- | --- |
| F-12 | 17.9% | 28.8 | 675 | 0.023 |
| F-14 | 13.0% | 24.8 | 383 | 0.015 |
| F-11 | 56.2% | 7.2 | 219 | 0.030 |
| F-1-C | 19.8% | 1.1 | 440 | 0.395 |
| F-15-D | 19.3% | 0.93 | 435 | 0.466 |
| F-5 | 10.1% | 0.24 | 219 | 0.907 |

Table 5.7: Oil-producing wellbores. “M bbl” here means million barrels.

- F-14 was the most efficient producer at 0.015 NPT hours per thousand barrels, with 13.0% NPT.

- F-12 produced the most oil (28.8 million barrels) at 17.9% NPT.

- F-11 lost 56.2% of its hours to NPT and still produced 7.2 million barrels.

- F-5 had low NPT (10.1%) but only 0.24 million barrels, the worst ratio. F-1-C and F-15-D are also high on this ratio. Hours per barrel is NPT hours divided by volume, so low-volume wells score badly almost by construction.

With only six wells, and F-11 the only high-NPT well among them, this supports a modest statement: in this field, NPT rate did not line up with output. It cannot show that NPT has no effect on production.

# 6. The Power BI Report

The report is built on the star schema and has five pages that share a header, a navigation bar, a blue/orange/slate palette and a rule that blue always means development and orange exploration.

| Page | Visuals | Message |
| --- | --- | --- |
| Headline | KPI cards (NPT %, total hours, NPT hours, NPT cost); hours-by-category donut with total in the centre; treemap of NPT by category; gauge against a 10% reference; annual trend line with a 20% average line | One in five rig hours was non-productive |
| Pareto | Column-and-line Pareto of NPT hours with cumulative %; top-1, top-2 and top-5 share cards; category table | Two categories own 62% of NPT |
| Wellbore | Ranked bar of NPT % by wellbore coloured by well type; parent-well and exploration slicers; worst / best NPT cards; sentence tooltips | A few short and exploratory wells have the worst rates |
| Cost | Bar of modelled NPT cost by wellbore; total, rig-rate and costliest-well cards | About $98.6M of modelled cost, concentrated in a few wells |
| NPT vs Production | Scatter of NPT % against cumulative oil, bubble size = cost, oil producers only; findings text | High NPT did not predict low output (small sample) |

Tooltips use Power BI’s sentence format so a hover reads as a plain sentence, for example “Wellbore F-12 ran at 17.9% NPT and produced 28.8M bbl”. The .pbix file embeds the imported data, so it opens anywhere, but Refresh only works on a machine that can reach the local PostgreSQL server.

Screenshots of each page can be exported from Power BI Desktop (File > Export > PDF) and inserted here.

# 7. Limitations and Assumptions

- The cost rate is an assumption. The $12,500 per hour used for every NPT hour is hard-coded in the SQL (v_npt_cost) and in the Power BI measure. No source for it is recorded in the repository, and the README describes a different method (published North Sea day rates with a spread multiplier) that the code does not implement. Treat the dollar figures as indicative; the ranking of categories and wells is the durable result. This should be reconciled before the cost figures are quoted externally.

- Two NPT % definitions exist. The report and Power BI divide by total logged hours (20.0% field-wide). The SQL view v_npt_by_wellbore divides by hours excluding rig moves (20.5% field-wide), which is why some earlier figures (for example 19-A at 41.0% and F-14 at 13.3%) are slightly higher than those here (38.4% and 13.0%). Standardising the view on one definition is a pending clean-up.

- Small production sample. Six wells have oil data. The NPT-versus-production comparison is descriptive and cannot support a statistical claim or any statement about cause.

- Classification involves judgement. Distinguishing planned from corrective work depends on narrative text. The audit quantifies the uncertainty (about ±0.2 percentage points on the headline) but cannot remove it. The manual review was done by one reviewer.

- Uneven time coverage. Drilling reports cover 1992–93, 1997–98 and 2007–2016 with gaps. Production data covers only 2007–2016 and 7 wellbores. Year-over-year comparisons mix very different campaigns.

- Percentages on short wells are volatile. Wells such as 19-B and F-11 have under 650 hours, so their rates swing widely. Read them together with absolute hours.

- Well identity is taken from file names. Rig-move days can be split across two well files, so a few hours may sit on the neighbouring wellbore.

- Production allocation. Volumes are the dataset’s allocated figures. Gaps of up to 85 days exist on two wells and were not interpolated.

# 8. Conclusions and Recommendations

## 8.1 Conclusions

- About 20% of logged rig time was non-productive, roughly 7,900 hours.

- Most NPT had causes that sit largely outside the well: equipment maintenance and weather explain 61% of it.

- NPT was concentrated: 13 wells carry 82% of the hours, and the extreme percentages belong to a few short or exploratory wellbores.

- In this field and this small sample, NPT rate did not track production output.

- The 20.0% figure rests on an audited classification, with a stated error rate and a stated residual uncertainty.

## 8.2 Recommendations

These follow from the data but are hypotheses for an operator to test, because the study is descriptive.

- Target surface-equipment reliability first. It is the largest single cause (36.9%). A preventive-maintenance review of rig and surface equipment has the highest potential payback.

- Plan for weather. At 24.5% of NPT, schedule weather-sensitive operations with contingency time and review seasonal planning.

- Treat the strike as an outlier. The 746 labour-action hours are one event. Remove them when benchmarking normal performance, and manage the contract risk separately.

- Review exploration and sidetrack planning. Exploration wellbores ran at 29.8% against 17.2%. The extra time is partly expected in unknown ground, but 19-A alone cost about $12.4M of modelled NPT.

- Judge wells by hours and output together. NPT percentage alone misleads on short wells; pair it with absolute hours and production volume.

## 8.3 Next steps for the project

- Standardise the NPT % definition in the SQL views and document the choice.

- Source or replace the $12,500 rate, and show cost as a range (low / base / high).

- Add more comparison data (other fields) before testing NPT against production statistically.

- Mine the narrative text to give root causes inside the large categories, such as which equipment failed.

# 9. Interview Preparation

Short answers to the questions this project is most likely to prompt. Numbers are from this report.

### 1. Give me the project in 60 seconds.

I took Equinor’s public Volve drilling reports, parsed about 23,000 logged activities, and classified each as productive, non-productive or rig move. I audited the classification by hand on 1,517 rows. I loaded the result into a PostgreSQL star schema and built a five-page Power BI report. About 20% of rig time was lost, 61% of that to equipment maintenance and weather, and high NPT did not coincide with low production in the six wells that have oil data.

### 2. How did you define NPT, and why not just use the source flag?

The source flag marks 3.2% of hours, while the interruption activity marks 21.2%, a sixfold gap. Neither is right on its own. I defined NPT by a taxonomy applied to the activity and its narrative, treated rig moves as a separate category, and used the source failure flag only as an override.

### 3. How do you know the classification is reliable?

I measured it. Confidence tiers were audited: 0% error on 150 high-confidence rows, 44% on medium, 93% on low. All low-confidence NPT rows were reviewed in full. Rule-only NPT was 21.7% and the audited figure is 20.0%, with at most about 0.2 points of NPT possibly hidden in the unreviewed remainder.

### 4. Why a star schema?

There are two fact tables at different grains (one row per activity, one row per well per day) that share wellbore and date dimensions. That lets one slicer filter both drilling and production, and it keeps measures simple.

### 5. Your report shows 20.0% in one place and 20.5% in another. Why?

Two denominators. The headline divides NPT hours by all logged hours (20.0%). One SQL view divides by hours excluding rig moves (20.5%). I caught it while validating the Power BI measures against the database. The fix is to standardise on one definition, which I chose to be total hours, and note it. Finding the difference during validation is the reason for validating.

### 6. Explain the cumulative-percentage DAX on the Pareto page.

For each bar it keeps the categories whose NPT hours are greater than or equal to the current bar and sums them, then divides by the total of all categories shown. ALLSELECTED gives the measure a list of every category in the visual, while still respecting slicers. SUMX and FILTER evaluate NPT Hours once per category, which is context transition.

### 7. How defensible is the $98.6M?

Not very, as an absolute number, and I say so. It is NPT hours times an assumed $12,500 per hour. The ranking of wells and causes holds for any constant rate, so I present the cost as indicative and would show a range with a sourced rate.

### 8. Did high NPT reduce production?

In this sample, no pattern showed it: F-11 lost 56% of its time and still produced 7.2 million barrels, while the largest producer ran at 18%. But only six wells have oil data, so I would not claim more than that. I would need more wells to test it properly.

### 9. What was the hardest data problem?

Telling planned work from corrective work. The same activity code, such as circulating or a sidetrack, can be productive or NPT depending on the narrative. That is why I built a confidence-tiered classifier and put a human in the loop for the uncertain rows.

### 10. What would you do next?

Standardise the NPT definition in SQL, source the day rate and show cost as a range, mine the narratives for root causes inside the big categories, and add other fields to test NPT against production with enough wells.

# Appendix A. Repository Structure

| Path | Contents |
| --- | --- |
| src/ | 00_download_selected.py, 01_inventory.py, 02_parse_production.py, 03_parse_drilling_reports.py, 04_classify_npt.py, 04b_apply_review.py, 05_load_to_postgres.py, build_wellbore_map.py |
| sql/ | 01_ddl_dimensions.sql, 02_ddl_facts.sql, 03_transforms.sql (views), 04_analysis_queries.sql |
| data/reference/ | wellbore_map.csv, npt_taxonomy.csv (versioned) |
| data/raw, data/interim | Local only (licence); parquet intermediates |
| docs/ | npt_taxonomy.md, quality reports, manual-review CSV, this report |
| powerbi/ | volve_npt.pbix and volve_theme.json |
| run_analysis.py | Runs the analysis queries against the database |

# Appendix B. Key DAX Measures

All measures live in the _Measures table. Table and column names are as in the model.

Total Hours      = SUM(fact_drilling_activity[hours])

NPT Hours        = CALCULATE([Total Hours], fact_drilling_activity[is_npt_final] = TRUE)

Rig Move Hours   = CALCULATE([Total Hours], dim_npt_category[is_rig_move] = TRUE)

Billable Hours   = CALCULATE([Total Hours], dim_npt_category[is_rig_move] = FALSE)

Productive Hours = [Billable Hours] - [NPT Hours]

NPT %            = DIVIDE([NPT Hours], [Total Hours])

Assumed Rig Rate = 12500

NPT Cost         = [NPT Hours] * [Assumed Rig Rate]

Cum Oil Bbl      = SUM(fact_daily_production[oil_bbl])

NPT Hrs per kbbl = DIVIDE([NPT Hours], [Cum Oil Bbl] / 1000)

% of Total NPT   = DIVIDE([NPT Hours],

CALCULATE([NPT Hours], ALL(dim_npt_category)))

Cumulative % =

VAR cur = [NPT Hours]

VAR tbl = ALLSELECTED(dim_npt_category[Category Label])

RETURN DIVIDE(

SUMX(FILTER(tbl, [NPT Hours] >= cur), [NPT Hours]),

SUMX(tbl, [NPT Hours]))

Top 2 Share =

DIVIDE(SUMX(TOPN(2, ALLSELECTED(dim_npt_category[Category Label]), [NPT Hours]), [NPT Hours]),

CALCULATE([NPT Hours], ALLSELECTED(dim_npt_category)))

Worst NPT %  = MAXX(ALLSELECTED(dim_wellbore[wellbore_key]), [NPT %])

Best NPT %   = MINX(ALLSELECTED(dim_wellbore[wellbore_key]), [NPT %])

Worst Well   = CONCATENATEX(TOPN(1, ALLSELECTED(dim_wellbore[wellbore_key]), [NPT %], DESC),

dim_wellbore[wellbore_key], ", ")

Calculated columns:

Category Label = dim_npt_category[level1] & " / " & dim_npt_category[level2]

Well Type      = IF(dim_wellbore[is_exploration], "Exploration", "Development")

# Appendix C. How to Reproduce

- Create the virtual environment, install requirements.txt and copy .env.example to .env with the database settings. Percent-encode the password with quote_plus because it can contain special characters.

- Obtain the Volve data under its licence and place it in data/raw (not committed).

- Run the numbered scripts in src/ in order (00 to 04b) to produce data/interim/drilling_activity_final.parquet.

- Run src/05_load_to_postgres.py to build the schema, load the tables and create the views.

- Open powerbi/volve_npt.pbix in Power BI Desktop. To refresh, point the PostgreSQL connection at your own server (localhost:5432, database volve_npt).

# Appendix D. Data Licence

The Volve dataset is released by Equinor ASA and the former Volve licence partners (ExxonMobil E&P Norway AS, Bayerngas Norge AS) “as is”, for study, research and development. This project is for educational and portfolio use and is non-commercial. Raw data is not redistributed. Check the original licence document that accompanies the dataset before publishing anything derived from it, including a public Power BI report, which embeds the data.